## AI Remediation Roadmap
Outline Level | Id | Name | Start | Finish | Duration | % Complete | Predecessors | Resources | Color | Notes
1 | 0 | Phase 1: Cognitive Visibility and AI Inference | 2025-05-12 | 2025-05-22 | 10 | 0 |  |  | SteelBlue
2 | 1 | Autonomous Cloud Graph Inference | 2025-05-12 | 2025-05-17 | 5 | 0 | 0 | SageMaker, Azure ML, Vertex AI | LightSkyBlue | Builds real-time AI cloud graph.
2 | 2 | Semantic Role Modeling | 2025-05-12 | 2025-05-17 | 5 | 0 | 1FS | OpenAI, Bedrock, IAM Analyzer | LightSkyBlue | Analyzes and refines IAM policy roles.
1 | 3 | Phase 2: Contextual Risk Modeling via AI Behavior Baselines | 2025-05-12 | 2025-05-24 | 12 | 0 |  |  | DarkOliveGreen
2 | 4 | AI Behavior Baseline Modeling | 2025-05-12 | 2025-05-18 | 6 | 0 | 2FS | GuardDuty, UEBA, BigQuery | YellowGreen | Models baseline behavior for control plane access.
2 | 5 | Cross-Cloud and Hybrid Pattern Matching | 2025-05-12 | 2025-05-18 | 6 | 0 | 4FS | LangChain, Vector DBs | YellowGreen | Uses embeddings to find cross-platform threats.
1 | 6 | Phase 3: Proactive Autonomous Policy Enforcement | 2025-05-12 | 2025-05-26 | 14 | 0 |  |  | SaddleBrown
2 | 7 | Dynamic Policy Generation | 2025-05-12 | 2025-05-19 | 7 | 0 | 5FS | LLM Agents, Firewall Manager | Tan | AI synthesizes SCPs and enforcement rules.
2 | 8 | AI-Guided Breakglass Governance | 2025-05-12 | 2025-05-19 | 7 | 0 | 7FS | Conditional Access, Lambda | Tan | Context-aware JIT access controls.
1 | 9 | Phase 4: Human-in-the-Loop Explainability & Forensics | 2025-05-12 | 2025-05-22 | 10 | 0 |  |  | DarkSlateBlue
2 | 10 | Explainable AI for Policy Decisions | 2025-05-12 | 2025-05-17 | 5 | 0 | 8FS | Bedrock, Azure OpenAI | MediumSlateBlue | Plain language explanations of AI decisions.
2 | 11 | Timeline Reconstruction via AI | 2025-05-12 | 2025-05-17 | 5 | 0 | 10FS | LangChain, TimeGPT | MediumSlateBlue | Reconstructs event chains from logs.
1 | 12 | Phase 5: Self-Healing Infrastructure-as-Code | 2025-05-12 | 2025-05-24 | 12 | 0 |  |  | DarkRed
2 | 13 | AI-Generated Infrastructure Patches | 2025-05-12 | 2025-05-18 | 6 | 0 | 11FS | Terraform, OPA, CloudFormation | LightCoral | AI writes validated infrastructure patches.
2 | 14 | Autonomous Red Teaming | 2025-05-12 | 2025-05-18 | 6 | 0 | 13FS | MITRE CALDERA, GPT Agents | LightCoral | Simulates metadata attack paths.